## Slide 1
ESR-LA IMPLEMENTATION TIMELINE(ALL)
*Study timelines depend on several factors and may be subject to change.
2025
2026
Today
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
100%
Sep 8 - Nov 6
60 days
ESR-LA-2
100%
Oct 20 - Dec 18
60 days
ESR-LA-3
100%
Oct 31 - Dec 29
60 days
ESR-LA-4
70%
Mar 15 - May 13
60 days
ESR-LA-DI2023
100%
Feb 9 - Apr 9
60 days
ESR-LA-5
10%
Apr 2 - May 31
60 days
ESR-LA-6
Apr 17 - Jun 15
ESR-LA-ERAS
60 days
ESR-LA-4 Kick-off
Oct 23
ESR-LA-DI2023 Kick-off
Dec 16
ESR-LA-5 Kick-off
Jan 6
ESR-LA-6 Kick-off
Jan 20
ESR-LA-ERAS Kick-off
Mar 10
ESR-LA-3 Kick-off
Oct 14
ESR-LA-2 Completion
Nov 7
0 days
0 days
0 days
0 days
0 days
0 days
0 days