OATT Attachment AQ Delivery Point Assessment Processes Guidelines

The purpose of the Delivery Point Assessment (DPA) process of Attachment AQ is to provide SPP Transmission Customers (TC) with a more efficient process for addition, modification, or retirement of delivery points.  This document provides the guidelines for interactions among the TC and SPP pertaining to the DPA process.

Requests for Delivery Point Assessment and Associated Timeline

STEP 1.  The TC submits request for change in Delivery Point Facilities to SPP and the Host Transmission Owner.

1. DPA requests shall be submitted if:
i. If it is a new, retired, or modified delivery point
ii. If there will be physical changes to delivery point facilities
2. The TC shall send the following items to SPP at loadstudies@spp.org. NOTE: Exclusion of any of these items will delay acceptance of DPA request for assessment.
i. Fully completed DPA Request Form (available at SPP Studies page on OASIS)
ii. Ten-year load forecast with Summer, Winter and Light loads for the delivery point being added or modified and any associated changes in the load forecast for other delivery points
iii. One-line diagram showing anticipated load and changes to local delivery facilities pertaining to the request
iv. Dynamic model files
v. Additional HILL Characteristics Form (SPP Business Practice 7850 or SPP page on Oasis)

STEP 2.  SPP shall perform initial assessment of the impacts of proposed change in Delivery Point, to determine if further study will be needed.
	
1. Results of preliminary assessment will be available to the applicant within 10 Business Days from the day of receipt of all required application materials.
2. All requests that have received a preliminary assessment during the prior calendar month will be posted on the studies section of the SPP OASIS by the 20th of the succeeding month.
3. If assessment result is that further study is required, SPP will initiate a Delivery Point Network Study (DPNS) Agreement with the TC.
4. If assessment result is that further study is not required, then the Host Transmission Owner will coordinate completion of all changes in delivery point facilities.

STEP 3.  If a DPNS is necessary, SPP shall enter into study agreement with the TC for the DPNS.

1. SPP will email the following items to the TC within 10 Business Days of receiving the DPA request:
i. Preliminary assessment result
ii. Potential scoping call dates and times
iii. Request for any additional information needed to complete DPNS study
iv. Notice that these items are due 30 days from when this email is sent.
2. TC shall provide SPP with the following items within 30 Calendar Days of receipt of the preliminary assessment:
i. Signed copy of the DPNS Agreement
ii. Any additional information requested by SPP.
3. If the TC fails to provide DPNS Agreement materials within 30 days of receipt of DPNS Agreement, Delivery Point Assessment request will be withdrawn unless otherwise agreed upon by both parties.

STEP 5.  SPP will perform the DPNS if needed.

1. After receiving the DPNS Agreement, materials, and hosting a scoping call between all parties, SPP will perform DPNS, assessing impacts on the Transmission System caused by adding or modifying a delivery point.  SPP will use power flow analysis and any other analysis that may be appropriate.
2. If the TC, Transmission Owner, or SPP identify changes in the delivery point assessment during the study, SPP will conduct any necessary restudy for the DPNS if acceptable to all parties.  This restudy would be at the expense of the TC.
3. Within 60 days (90 days if HILL) the scoping call and receipt of all necessary materials, SPP will complete the study and send the DPNS report to the TC.
i. If SPP is unable to complete and deliver the study within the study window, they shall provide an explanation to TC and Host Transmission Owner regarding the cause(s) of delay and a revised completion date.
4. After the study has completed, SPP will either:
i. Bill the TC for study costs and the non-refundable application fee.
ii.  Any balance due shall be paid within 30 days of billing.

STEP 6.  Coordination of Study Results and Impact Mitigation

1. SPP and the Transmission Owner shall coordinate transmission facility upgrades if upgrades are needed.
i. Transmission Owner shall notify SPP when official agreement has been reached between TC and TO regarding load connection facility upgrades.
2. SPP will issue a Notification to Construct (NTC) to the Transmission Owner if transmission facilities must be installed.
3. The delivery point facilities, as modified, should not be connected to the Transmission System until SPP has authorized such connection.
i. In accordance with its NTC, each affected Transmission Owner shall notify SPP in writing or email that all facilities it has been required to install are completed (a certificate of commercial operation).
ii. SPP will inform TC of when such notification has been provided by all affected transmission owners.


END OF AQ PROCESS


STEP 7.  Planning Model Integration

1. After the end of the AQ process, any new, modified, or retired delivery point with accompanying transmission facilities will be migrated into all SPP planning models under the following conditions:
i. Upon completion of preliminary assessment concluding that no further SPP study is required 
—OR—
ii. Upon completion of DPNS report.
—AND—
iii. The TC has notified SPP and the Host Transmission Owner that the Delivery Point change is proceeding/updating a Service Agreement.
2. The Host TO will be responsible for coordinating and ensuring the Model on Demand (MOD) information is submitted through the MOD portal for each applicable DPA request. 






This document describes the procedures for the Delivery Point Assessment process. This procedure document does not relieve the TC’s responsibility for reading, understanding and adhering to the SPP OATT.	

